## Sheet1
Facility Name: |  |  | SRN: |  | Pre-Application Meeting Date:
Due Date:
Task | Timeline Recommendation |  | Proposed Submittal Date / Date Received | Date Completed | Comments
Application to be submitted | 12 | months prior to expiration | 00/00/0000 | 00/00/0000
Administrative Completeness Check | 15 | calendar days | #VALUE!
Technical Review Complete -- including all additional information requests and completion of draft staff report and working draft ROP | 7 | months | #VALUE!
Company Review Working Draft ROP | 21 | calendar days (21-30 day review) | #VALUE!
Address Company Comments Convert Working Draft ROP to Draft ROP, Finalize Staff Report | 14 | calendar days | #VALUE!
Post Public Notice/Calendar Notice | 7 | calendar days | #VALUE!
Public Comment/Affected States Review (Draft Permit) | 30 | calendar days | #VALUE!
Public Hearing if requested | 0 | calendar days (45 days if requested) | #VALUE!
Revisions/Company Review (if needed). Convert Draft ROP to Proposed ROP, Add addendum to Staff Report | 16 | calendar days | #VALUE!
EPA Review (Proposed Permit) | 45 | calendar days | #VALUE!
Issue Permit | 5 | calendar days | #VALUE!