## Project 1
Completed? | Project Details | Due By | Notes
| Propose optimal corrosion control treatment, or a corrosion study | 2019-03-31 | Action Level Exceedance (ALE) Requirement
| Submit rate study to DEQ with implementation plan | 2019-04-01 | Still need a plan to implement rate increases as recommended by the study
| Obtain licensed operator in charge of water distribution system | 2019-05-01
| Submit plan to streamline the rate collection process | 2019-05-01
| Upgrade existing SCADA system to have historian and alarm capabilities | 2019-05-15
| Fix continuous chlorine analyzer | 2019-05-15
| Submit updated cross connection control program, staffing support | 2019-06-01
| Submit plan to inventory valves, and plan for ongoing maintenance | 2019-06-01
| Install coagulant feed to rapid mix | 2019-06-01
| Install metering capabilities | 2019-06-15
| Collect 60 samples for lead and copper, remembering 1st/5th liter | 2019-06-30 | Action Level Exceedance (ALE) Requirement
| Collect WQP as required by ALE letter | 2019-06-30 | Action Level Exceedance (ALE) Requirement
| Conduct professional inspection of water tower | 2019-06-30
| Install working mussel feed control system at the raw water intake | 2019-06-30
| Report 2018 ALE in the consumer confidence Report | 2019-07-01 | Action Level Exceedance (ALE) Requirement
| For first round of 2019, this is the due date for reporting to DEQ | 2019-09-28 | Action Level Exceedance (ALE) Requirement
| Collect 60 samples for lead and copper, remembering 1st/5th liter | 2019-12-31 | Action Level Exceedance (ALE) Requirement
| Collect WQP as required by ALE letter | 2019-12-31 | Action Level Exceedance (ALE) Requirement
| Repair filter to waste valves | 2020-01-01
| For second round of 2019, this is the due date for reporting to DEQ | 2020-03-31 | Action Level Exceedance (ALE) Requirement
| Collect one LCR sample from entry point to distribution | 2022-03-31 | Action Level Exceedance (ALE) Requirement