## Project 1
Completed? | Project Details | Due By | Notes
| Install metering capabilities | 2019-12-15 | ACO. Extended due to lead time on meter and logistics
| Submit Lead Consumer Notice for 1st round of sampling in 2019 | 2019-12-21 | Reporting violation letter dated November 21, 2019
| Submit rate collection plan | 2019-12-31 | ACO.
| Collect 60 samples for lead and copper, remembering 1st/5th liter | 2019-12-31 | Action Level Exceedance (ALE) Requirement
| Collect 10 WQP distribution samples as required by ALE letter | 2019-12-31 | Action Level Exceedance (ALE) Requirement
| Collect Synthetic Organic Compound sample (SOC) | 2019-12-31 | quarterly monitoring
| Report Lead and copper samples & WQPs taken by 12/31/2019 | 2020-01-10 | Action Level Exceedance (ALE) Requirement
| Submit updated cross connection control program, staffing support | 2020-03-31 | ACO. Ensure adequate staffing or contract support for program
| Send Consumer Notice of lead and copper, and sample of the notice | 2020-03-31 | Action Level Exceedance (ALE) Requirement
| Collect 10 WQP distribution samples as required by ALE letter | 2020-03-31 | Action Level Exceedance (ALE) Requirement
| Collect Synthetic Organic Compound sample (SOC) | 2020-03-31 | quarterly monitoring
| Install working mussel feed control system at the raw water intake | 2020-04-01 | ACO. Submit permit application by 3/1/2020
| Submit plan to inventory valves, and plan for ongoing maintenance | 2020-06-30 | ACO.
| Collect 60 samples for lead and copper, remembering 1st/5th liter | 2020-06-30 | Action Level Exceedance (ALE) Requirement
| Collect 10 WQP distribution samples as required by ALE letter | 2020-06-30 | Action Level Exceedance (ALE) Requirement
| Collect Synthetic Organic Compound sample (SOC) | 2020-06-30 | quarterly monitoring
| Submit plan to implement rate increases | 2020-07-01 | ACO.
| CCR is due | 2020-07-01 | All violations and ALE's from 2019 must be included. Submit draft for EGLE review is needed.
| Report Lead and copper samples & WQPs taken by 7/1/2020 | 2020-07-10 | Action Level Exceedance (ALE) Requirement
| Repair filter to waste valves | 2020-09-01 | ACO.
| Send Consumer Notice of lead and copper, and sample of the notice | 2020-09-29 | Action Level Exceedance (ALE) Requirement
| Collect 10 WQP distribution samples as required by ALE letter | 2020-09-30 | Action Level Exceedance (ALE) Requirement
| Collect Synthetic Organic Compound sample (SOC) | 2020-09-30 | quarterly monitoring
| Annual Compliance Monitoring Due | 2020-09-30 | See monitoring schedule for 2020.
| Annual Fee Due | 2020-11-30
| Collect Synthetic Organic Compound sample (SOC) | 2020-12-31 | quarterly monitoring
| Conduct professional inspection of water tower | 2020-12-31 | ACO. Delayed pending approval to conduct work through DWRF
| Collect one LCR sample from entry point to distribution | 2022-03-31 | Action Level Exceedance (ALE) Requirement