## Sheet1
EXHIBIT A
ACO Compliance Timeline Progress Summary for City of Benton Harbor
Item | Initial Deadline | Extended Deadline | Extension History
Submit a rate study | 2019-04-01 | (completed)
Upgrade SCADA system for data access and storage | 2019-04-01 | (completed) | 1-from 4/1/19 to 5/15/19
Install continuous chlorine analyzer on WTP tap | 2019-04-01 | (completed) | 1-from 4/1/19 to 5/15/19
Corrosion Treatment Study | 2019-04-01 | (completed)
Distribution Operator in charge | 2019-04-01 | (completed) | 1-from 4/1/19 to 5/1/19 2-from 5/1/19 to 5/22/19
Permit and Construct coagulant feed to existing rapid mix | 2019-06-01 | (completed) | 1-from 6/1/19 to 8/2/19
Submit plan to implement rate increases | 2019-04-01 | 2020-07-01 | 1-from 4/1/19 to 9/30/19 2-from 9/30/19 to 7/1/20
Install flow meter on finished water | 2019-04-01 | 2019-12-15 | 1-from 4/1/19 to 6/15/19 2-from 6/15/19 to 9/30/19 3-from 9/30/19 to 12/15/19 4-request not granted
Submit updated rate collections plan | 2019-05-01 | 2019-12-31 | 1-from 5/1/19 to 9/30/19 2-from 9/30/19 to 12/31/19 Deadline not met
Updated cross connection program including residential accounts | 2019-06-01 | 2020-03-31 | 1-from 6/1/19 to 12/31/19
Submit maintenance plan for valves and hydrants | 2019-06-01 | 2020-06-30 | 1-from 6/1/19 to 9/30/19 2-from 9/30/19 to 6/30/20
Conduct professional inspection of water tower, or conduct cleaning and repaint interior | 2019-06-30 | 2020-12-31 | 1-from 6/30/19 to 12/31/19 2-from 12/31/19 to 12/31/20
Install/repair mussel control system at intake | 2019-06-30 | 2020-04-01 | 1-from 6/30/19 to 12/31/19 2-from 12/31/19 to 3/1/20
Repair filter to waste valves | 2020-01-31 | 2020-09-01 | 1-from 1/31/20 to 9/1/20